## LEMs
Site | Subsystem | SSM # | Software Build | Scheduled | Start | Complete
ZDC | WMS | SSM-WAAS-057 | W7.297L | 2020-05-09 18:00 | 2020-05-09 17:49 | 2020-05-09 20:42
ZDC | WMS | SSM-WAAS-054 | Hardware | 2020-05-09 18:00 | 2020-05-09 18:10 | 2020-05-09 20:42
DCC | WOMS | SSM-WAAS-054 | W7.296L
SCT | WOMS | SSM-WAAS-054 | W7.296L
ZLA | WMS | SSM-WAAS-054 | Hardware | 2020-05-06 04:00 | 2020-05-06 04:22 | 2020-05-06 07:42
ZLA | WMS | SSM-WAAS-057 | W7.297L | 2020-05-06 04:00 | 2020-05-06 04:03 | 2020-05-06 07:42
CMA | SGS | SSM-WAAS-054 | W7.296L
DXR | SGS | SSM-WAAS-054 | W7.296L
QWE | SGS | SSM-WAAS-054 | W7.296L
S97 | SGS | SSM-WAAS-054 | W7.296L
S97A | SGS | SSM-WAAS-054 | W7.296L
SZPA | SGS | SSM-WAAS-054 | W7.296L
APC | SGS | SSM-WAAS-054 | W7.296L
S97B | SGS | SSM-WAAS-054 | W7.296L
TJX | WCN | SSM-WAAS-054 | W7.296L
ZAU | WCN | SSM-WAAS-054 | W7.296L
ZDC | WCN | SSM-WAAS-054 | W7.296L
ZLA | WCN | SSM-WAAS-054 | W7.296L
ZSE | WCN | SSM-WAAS-054 | W7.296L
ZTL | WCN | SSM-WAAS-054 | W7.296L
ZTL | WMS | SSM-WAAS-057 | W7.297L | 2020-05-12 18:00 | 2020-05-12 18:36 | 2020-05-12 23:15
ZTL | WMS | SSM-WAAS-054 | Hardware | 2020-05-12 18:00 | 2020-05-12 20:02 | 2020-05-12 23:15
BET | WRS | SSM-WAAS-057 | W7.297L
BIL | WRS | SSM-WAAS-057 | W7.297L
BRW | WRS | SSM-WAAS-057 | W7.297L
CDB | WRS | SSM-WAAS-057 | W7.297L
FAI | WRS | SSM-WAAS-057 | W7.297L | 2020-05-18 16:00 | 2020-05-18 13:44 | 2020-05-19 16:36
HNL | WRS | SSM-WAAS-057 | W7.297L
ZDV | WRS | SSM-WAAS-057 | W7.297L | 2020-05-18 18:00 | 2020-05-18 17:02 | 2020-05-19 01:42
OTZ | WRS | SSM-WAAS-057 | W7.297L
Q9A | WRS | SSM-WAAS-057 | W7.297L
Q9B | WRS | SSM-WAAS-057 | W7.297L
Q9C | WRS | SSM-WAAS-057 | W7.297L
Q9D | WRS | SSM-WAAS-057 | W7.297L
Q9E | WRS | SSM-WAAS-057 | W7.297L
YFB | WRS | SSM-WAAS-057 | W7.297L
YQX | WRS | SSM-WAAS-057 | W7.297L
YWG | WRS | SSM-WAAS-057 | W7.297L
YYR | WRS | SSM-WAAS-057 | W7.297L
ZAN | WRS | SSM-WAAS-057 | W7.297L | 2020-05-19 22:00 | 2020-05-19 13:29 | 2020-05-20 22:22
ZJX | WRS | SSM-WAAS-057 | W7.297L | 2020-05-20 11:00 | 2020-05-20 11:19 | 2020-05-21 00:11
JNU | WRS | SSM-WAAS-057 | W7.297L | 2020-05-20 16:00 | 2020-05-20 17:08 | 2020-05-21 13:53
ZBW | WRS | SSM-WAAS-057 | W7.297L
ZDC | WRS | SSM-WAAS-057 | W7.297L
ZSU | WRS | SSM-WAAS-057 | W7.297L | 2020-05-21 10:43 | 2020-05-21 11:33
ZKC | WRS | SSM-WAAS-057 | W7.297L | 2020-05-25 14:00
ZAU | WRS | SSM-WAAS-057 | W7.297L | 2020-05-26 12:00
ZAB | WRS | SSM-WAAS-057 | W7.297L | 2020-05-26 14:00
ZHU | WRS | SSM-WAAS-057 | W7.297L | 2020-05-28 01:00
ZLA | WRS | SSM-WAAS-057 | W7.297L
ZLC | WRS | SSM-WAAS-057 | W7.297L
ZMA | WRS | SSM-WAAS-057 | W7.297L
ZME | WRS | SSM-WAAS-057 | W7.297L
ZMP | WRS | SSM-WAAS-057 | W7.297L
ZNY | WRS | SSM-WAAS-057 | W7.297L
ZOA | WRS | SSM-WAAS-057 | W7.297L | 2020-05-28 14:00
ZOB | WRS | SSM-WAAS-057 | W7.297L
ZSE | WRS | SSM-WAAS-057 | W7.297L
ZFW | WRS | SSM-WAAS-057 | W7.297L | 2020-05-29 15:00
ZTL | WRS | SSM-WAAS-057 | W7.297L
APC | SGS | SSM-WAAS-056 | N/A
SCT | WOMS | SSM-WAAS-056 | N/A

## Operator Action Logs
Time | O&M | Action | Description | Activity
2020-05-06T03:52:34 | NOC | Update Approved SW Version | Update Approved Software Versions command successful. | ZLA WMS Upgrade
2020-05-06T03:55:33 | POC | Update Approved SW Version | Update Approved Software Versions command successful. | ZLA WMS Upgrade
2020-05-06T04:02:55 | POC | Software Configuration Check | Operator selected W7.297L as the next startup version at ZLA WMS CV . | ZLA WMS Upgrade
2020-05-06T04:07:30 | NOC | Change Remote Mode | POC WMS OM NORMAL MAINTENANCE | ZLA WMS Upgrade
2020-05-06T04:07:51 | NOC | Shutdown | node POC WMS OM mode 3 | ZLA WMS Upgrade
2020-05-06T04:15:32 | NOC | Control Power | POC WMS OM Off | ZLA WMS Upgrade
2020-05-06T04:16:56 | NOC | Change CV Mode | ZLA WMS CV NORMAL MAINTENANCE | ZLA WMS Upgrade
2020-05-06T04:17:35 | NOC | Shutdown | node ZLA WMS CV mode 3 | ZLA WMS Upgrade
2020-05-06T04:22:15 | NOC | Control Power | ZLA WMS CV Off | ZLA WMS Upgrade
2020-05-06T06:05:10 | NOC | Control Power | ZLA WMS CV On | ZLA WMS Upgrade
2020-05-06T06:06:18 | NOC | Control Power | POC WMS OM On | ZLA WMS Upgrade
2020-05-06T06:37:47 | NOC | Transfer CV Warm Start Data | Download warm start data completed successfully | ZLA WMS Upgrade
2020-05-06T06:38:16 | NOC | Restart | node ZLA WMS CV mode 3 current version W7.297L | ZLA WMS Upgrade
2020-05-06T06:40:24 | NOC | Change Remote Mode | POC WMS OM VERIFICATION NORMAL | ZLA WMS Upgrade
2020-05-06T07:42:30 | NOC | Change CV Mode | ZLA WMS CV VERIFICATION NORMAL | ZLA WMS Upgrade
2020-05-09 17:49 | NOC | Software Configuration Check | Operator selected W7.297L as the next startup version at ZDC WMS CV . | ZDC WMS Upgrade
2020-05-09 18:04 | NOC | Change CV Mode | Mode change from NORMAL to MAINTENANCE at ZDC WMS CV initiated. | ZDC WMS Upgrade
2020-05-09 18:04 | NOC | Change CV Mode | CV subsystem mode change command at ZDC WMS CV successful. | ZDC WMS Upgrade
2020-05-09 18:04 | NOC | Shutdown | node ZDC WMS CV mode 3 | ZDC WMS Upgrade
2020-05-09 18:10 | NOC | Control Power | ZDC WMS CV Off | ZDC WMS Upgrade
2020-05-09 19:19 | NOC | Control Power | No response to Control Power at ZDC WMS CV . | ZDC WMS Upgrade
2020-05-09 19:20 | NOC | Control Power | ZDC WMS CV On | ZDC WMS Upgrade
2020-05-09 19:52 | NOC | Transfer CV Warm Start Data | Executing download cv warm start data from ZTL WMS CV to ZDC WMS CV of files: /waas/WAAS_WARM_ | ZDC WMS Upgrade
2020-05-09 19:53 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ICBM_WARMSTART_0002.dat transferred successfully on cp1 | ZDC WMS Upgrade
2020-05-09 19:53 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ICBM_WARMSTART_0002.dat.crc transferred successfully on cp1 | ZDC WMS Upgrade
2020-05-09 19:53 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ICID_WARMSTART_0001.dat transferred successfully on cp1 | ZDC WMS Upgrade
2020-05-09 19:56 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ODOT_WARMSTART_0009.dat transferred successfully on cp1 | ZDC WMS Upgrade
2020-05-09 19:56 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ICBM_WARMSTART_0002.dat transferred successfully on cp2 | ZDC WMS Upgrade
2020-05-09 19:57 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ICID_WARMSTART_0001.dat transferred successfully on cp2 | ZDC WMS Upgrade
2020-05-09 19:57 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ICID_WARMSTART_0001.dat.crc transferred successfully on cp2 | ZDC WMS Upgrade
2020-05-09 20:00 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ODOT_WARMSTART_0009.dat transferred successfully on cp2 | ZDC WMS Upgrade
2020-05-09 20:00 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ODOT_WARMSTART_0009.dat.crc transferred successfully on cp2 | ZDC WMS Upgrade
2020-05-09 20:00 | NOC | Transfer CV Warm Start Data | Download warm start data completed successfully | ZDC WMS Upgrade
2020-05-09 20:01 | NOC | Restart | node ZDC WMS CV mode 3 current version W7.297L | ZDC WMS Upgrade
2020-05-09 20:05 | NOC | Change CV Mode | Mode change from MAINTENANCE to VERIFICATION at ZDC WMS CV initiated. | ZDC WMS Upgrade
2020-05-09 20:05 | NOC | Change CV Mode | CV subsystem mode change command at ZDC WMS CV successful. | ZDC WMS Upgrade
2020-05-09 20:36 | NOC | Change CV Mode | Mode change from VERIFICATION to MAINTENANCE at ZDC WMS CV initiated. | ZDC WMS Upgrade
2020-05-09 20:36 | NOC | Change CV Mode | CV subsystem mode change command at ZDC WMS CV successful. | ZDC WMS Upgrade
2020-05-09 20:36 | NOC | Change CV Mode | Mode change from MAINTENANCE to VERIFICATION at ZDC WMS CV initiated. | ZDC WMS Upgrade
2020-05-09 20:36 | NOC | Change CV Mode | CV subsystem mode change command at ZDC WMS CV successful. | ZDC WMS Upgrade
2020-05-09 20:42 | NOC | Change CV Mode | Mode change from VERIFICATION to NORMAL at ZDC WMS CV initiated. | ZDC WMS Upgrade
2020-05-09 20:42 | NOC | Change CV Mode | CV subsystem mode change command at ZDC WMS CV successful. | ZDC WMS Upgrade
2020-05-12 18:36 | NOC | Software Configuration Check | Operator selected W7.297L as the next startup version at ZTL WMS CV . | ZTL WMS Upgrade
2020-05-12 20:01 | NOC | Change CV Mode | Mode change from NORMAL to MAINTENANCE at ZTL WMS CV initiated. | ZTL WMS Upgrade
2020-05-12 20:01 | NOC | Change CV Mode | CV subsystem mode change command at ZTL WMS CV successful. | ZTL WMS Upgrade
2020-05-12 20:01 | NOC | Shutdown | node ZTL WMS CV mode 3 | ZTL WMS Upgrade
2020-05-12 20:02 | NOC | Control Power | ZTL WMS CV Off | ZTL WMS Upgrade
2020-05-12 21:50 | NOC | Control Power | ZDC WMS CV Off | Cancelled before command executed
2020-05-12 21:51 | NOC | Control Power | ZTL WMS CV On | ZTL WMS Upgrade
2020-05-12 22:13 | NOC | Transfer CV Warm Start Data | Executing download cv warm start data from ZLA WMS CV to ZTL WMS CV of files: /waas/WAAS_WARM_ | ZTL WMS Upgrade
2020-05-12 22:13 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ICBM_WARMSTART_0002.dat transferred successfully on cp1 | ZTL WMS Upgrade
2020-05-12 22:13 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ICBM_WARMSTART_0002.dat.crc transferred successfully on cp1 | ZTL WMS Upgrade
2020-05-12 22:14 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ICID_WARMSTART_0001.dat transferred successfully on cp1 | ZTL WMS Upgrade
2020-05-12 22:17 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ODOT_WARMSTART_0009.dat transferred successfully on cp1 | ZTL WMS Upgrade
2020-05-12 22:18 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ODOT_WARMSTART_0009.dat.crc transferred successfully on cp1 | ZTL WMS Upgrade
2020-05-12 22:18 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ICBM_WARMSTART_0002.dat transferred successfully on cp2 | ZTL WMS Upgrade
2020-05-12 22:18 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ICBM_WARMSTART_0002.dat.crc transferred successfully on cp2 | ZTL WMS Upgrade
2020-05-12 22:19 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ICID_WARMSTART_0001.dat transferred successfully on cp2 | ZTL WMS Upgrade
2020-05-12 22:19 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ICID_WARMSTART_0001.dat.crc transferred successfully on cp2 | ZTL WMS Upgrade
2020-05-12 22:22 | NOC | Transfer CV Warm Start Data | Warm start file WAAS_CV_ODOT_WARMSTART_0009.dat transferred successfully on cp2 | ZTL WMS Upgrade
2020-05-12 22:22 | NOC | Transfer CV Warm Start Data | Download warm start data completed successfully | ZTL WMS Upgrade
2020-05-12 22:24 | NOC | Restart | node ZTL WMS CV mode 3 current version W7.297L | ZTL WMS Upgrade
2020-05-12 22:29 | NOC | Change CV Mode | Mode change from MAINTENANCE to VERIFICATION at ZTL WMS CV initiated. | ZTL WMS Upgrade
2020-05-12 22:29 | NOC | Change CV Mode | CV subsystem mode change command at ZTL WMS CV successful. | ZTL WMS Upgrade
2020-05-12 23:15 | NOC | Change CV Mode | Mode change from VERIFICATION to NORMAL at ZTL WMS CV initiated. | ZTL WMS Upgrade
2020-05-12 23:15 | NOC | Change CV Mode | CV subsystem mode change command at ZTL WMS CV successful. | ZTL WMS Upgrade
2020-05-18 14:25 | POC | Download | Downloading version W7.297L to subsystem FAI WRS WRE-C | FAI WRS Upgrade
2020-05-18 15:04 | POC | Download | Download CKS file DCP.cks verification successful | FAI WRS Upgrade
2020-05-18 15:04 | POC | Download | Download process completed for subsystem FAI WRS WRE-C | FAI WRS Upgrade
2020-05-18 15:06 | POC | Delete Build | Deleting Software Build version W7.224L at FAI WRS WRE-C | FAI WRS Upgrade
2020-05-18 15:06 | POC | Delete Build | Delete Software Build command successful. | FAI WRS Upgrade
2020-05-18 15:07 | POC | Download | Downloading router config file version 05 to subsystem FAI WRS ACS-A | FAI WRS Upgrade
2020-05-18 15:07 | POC | Download | Download command at FAI WRS ACS-A successful. | FAI WRS Upgrade
2020-05-18 15:09 | POC | Download | Downloading router config file version 05 to subsystem FAI WRS ACS-B | FAI WRS Upgrade
2020-05-18 15:10 | POC | Download | Download command at FAI WRS ACS-B successful. | FAI WRS Upgrade
2020-05-18 15:12 | POC | Reset | FAI WRS ACS-A | FAI WRS Upgrade
2020-05-18 15:18 | POC | Reset | FAI WRS ACS-B | FAI WRS Upgrade
2020-05-18 15:52 | POC | Software Configuration Check | Operator selected W7.297L as the next startup version at FAI WRS WRE-C. | FAI WRS Upgrade
2020-05-18 15:59 | POC | Change WRE Mode | FAI WRS WRE-C NORMAL MAINTENANCE | FAI WRS Upgrade
2020-05-18 16:00 | POC | Restart | node FAI WRS WRE-C mode 3 current version W7.235L | FAI WRS Upgrade
2020-05-18 16:19 | POC | Change WRE Mode | FAI WRS WRE-C MAINTENANCE VERIFICATION | FAI WRS Upgrade
2020-05-18 16:48 | POC | Download | Downloading version W7.297L to subsystem FAI WRS WRE-B | FAI WRS Upgrade
2020-05-18 16:49 | POC | Download | Download command cancelled for subsystem FAI WRS WRE-B | FAI WRS Upgrade
2020-05-18 16:55 | POC | Change WRE Mode | FAI WRS WRE-C VERIFICATION NORMAL | FAI WRS Upgrade
2020-05-18 16:56 | POC | Download | Downloading version W7.297L to subsystem FAI WRS WRE-B | FAI WRS Upgrade
2020-05-18 16:58 | POC | Download | Download command cancelled for subsystem FAI WRS WRE-B | FAI WRS Upgrade
2020-05-18 17:03 | POC | Download | Downloading router config file version 08 to subsystem ZDV WRS ACS-A | ZDV WRS Upgrade
2020-05-18 17:03 | POC | Download | Download command at ZDV WRS ACS-A successful. | ZDV WRS Upgrade
2020-05-18 17:03 | POC | Download | Downloading router config file version 08 to subsystem ZDV WRS ACS-B | ZDV WRS Upgrade
2020-05-18 17:04 | POC | Download | Download command at ZDV WRS ACS-B successful. | ZDV WRS Upgrade
2020-05-18 17:05 | POC | Download | Downloading version W7.297L to subsystem ZDV WRS WRE-C | ZDV WRS Upgrade
2020-05-18 17:34 | POC | Download | Download CKS file DCP.cks verification successful | ZDV WRS Upgrade
2020-05-18 17:34 | POC | Download | Download process completed for subsystem ZDV WRS WRE-C | ZDV WRS Upgrade
2020-05-18 17:48 | POC | Reset | ZDV WRS ACS-A | ZDV WRS Upgrade
2020-05-18 17:53 | POC | Reset | ZDV WRS ACS-B | ZDV WRS Upgrade
2020-05-18 17:57 | POC | Delete Build | Deleting Software Build version W7.224L at ZDV WRS WRE-C | ZDV WRS Upgrade
2020-05-18 17:57 | POC | Delete Build | Delete Software Build command successful. | ZDV WRS Upgrade
2020-05-18 17:57 | POC | Software Configuration Check | Operator selected W7.297L as the next startup version at ZDV WRS WRE-C. | ZDV WRS Upgrade
2020-05-18 18:00 | POC | Change WRE Mode | Mode change from NORMAL to MAINTENANCE at ZDV WRS WRE-C initiated. | ZDV WRS Upgrade
2020-05-18 18:01 | POC | Restart | node ZDV WRS WRE-C mode 3 current version W7.235L | ZDV WRS Upgrade
2020-05-18 18:02 | NOC | Download | Downloading version W7.297L to subsystem FAI WRS WRE-B | FAI WRS Upgrade
2020-05-18 18:22 | NOC | Download | Download CKS file DCP.cks verification successful | FAI WRS Upgrade
2020-05-18 18:22 | NOC | Download | Download process completed for subsystem FAI WRS WRE-B | FAI WRS Upgrade
2020-05-18 18:22 | POC | Change WRE Mode | Mode change from MAINTENANCE to VERIFICATION at ZDV WRS WRE-C initiated. | ZDV WRS Upgrade
2020-05-18 18:24 | NOC | Download | Downloading version W7.297L to subsystem FAI WRS WRE-A | FAI WRS Upgrade
2020-05-18 18:45 | NOC | Download | Download CKS file DCP.cks verification successful | FAI WRS Upgrade
2020-05-18 18:45 | NOC | Download | Download process completed for subsystem FAI WRS WRE-A | FAI WRS Upgrade
2020-05-18 18:49 | POC | Change WRE Mode | Mode change from VERIFICATION to NORMAL at ZDV WRS WRE-C initiated. | ZDV WRS Upgrade
2020-05-18 19:11 | POC | Download | Downloading version W7.297L to subsystem ZDV WRS WRE-B | ZDV WRS Upgrade
2020-05-18 19:12 | POC | Delete Build | Deleting Software Build version W7.224L at FAI WRS WRE-B | FAI WRS Upgrade
2020-05-18 19:12 | POC | Delete Build | Delete Software Build command successful. | FAI WRS Upgrade
2020-05-18 19:12 | POC | Delete Build | Deleting Software Build version W7.224L at FAI WRS WRE-A | FAI WRS Upgrade
2020-05-18 19:12 | POC | Delete Build | Delete Software Build command successful. | FAI WRS Upgrade
2020-05-18 19:28 | POC | Download | Download CKS file DCP.cks verification successful | FAI WRS Upgrade
2020-05-18 19:28 | POC | Download | Download process completed for subsystem ZDV WRS WRE-B | ZDV WRS Upgrade
2020-05-18 19:31 | POC | Delete Build | Deleting Software Build version W7.224L at ZDV WRS WRE-B | ZDV WRS Upgrade
2020-05-18 19:31 | POC | Delete Build | Delete Software Build command successful. | ZDV WRS Upgrade
2020-05-18 19:31 | NOC | Download | Downloading version W7.297L to subsystem ZDV WRS WRE-A | ZDV WRS Upgrade
2020-05-18 19:33 | POC | Software Configuration Check | Operator selected W7.297L as the next startup version at FAI WRS WRE-B. | FAI WRS Upgrade
2020-05-18 19:35 | POC | Change WRE Mode | FAI WRS WRE-B NORMAL MAINTENANCE | FAI WRS Upgrade
2020-05-18 19:35 | POC | Restart | node FAI WRS WRE-B mode 3 current version W7.235L | FAI WRS Upgrade
2020-05-18 19:50 | NOC | Download | Download CKS file DCP.cks verification successful | FAI WRS Upgrade
2020-05-18 19:50 | NOC | Download | Download process completed for subsystem ZDV WRS WRE-A | ZDV WRS Upgrade
2020-05-18 19:55 | POC | Change WRE Mode | FAI WRS WRE-B MAINTENANCE VERIFICATION | FAI WRS Upgrade
2020-05-18 20:04 | POC | Delete Build | Deleting Software Build version W7.224L at ZDV WRS WRE-A | ZDV WRS Upgrade
2020-05-18 20:04 | POC | Delete Build | Delete Software Build command successful. | ZDV WRS Upgrade
2020-05-18 20:23 | POC | Change WRE Mode | FAI WRS WRE-B VERIFICATION NORMAL | FAI WRS Upgrade
2020-05-18 23:09 | NOC | Software Configuration Check | Operator selected W7.297L as the next startup version at ZDV WRS WRE-B. | ZDV WRS Upgrade
2020-05-18 23:09 | NOC | Change WRE Mode | Mode change from NORMAL to MAINTENANCE at ZDV WRS WRE-B initiated. | ZDV WRS Upgrade
2020-05-18 23:10 | NOC | Restart | node ZDV WRS WRE-B mode 3 current version W7.235L | ZDV WRS Upgrade
2020-05-18 23:28 | NOC | Change WRE Mode | Mode change from MAINTENANCE to VERIFICATION at ZDV WRS WRE-B initiated. | ZDV WRS Upgrade
2020-05-18 23:54 | NOC | Change WRE Mode | Mode change from VERIFICATION to NORMAL at ZDV WRS WRE-B initiated. | ZDV WRS Upgrade
2020-05-19 01:06 | NOC | Software Configuration Check | Operator selected W7.297L as the next startup version at ZDV WRS WRE-A. | ZDV WRS Upgrade
2020-05-19 01:07 | NOC | Change WRE Mode | Mode change from NORMAL to MAINTENANCE at ZDV WRS WRE-A initiated. | ZDV WRS Upgrade
2020-05-19 01:07 | NOC | Restart | node ZDV WRS WRE-A mode 3 current version W7.235L | ZDV WRS Upgrade
2020-05-19 01:24 | NOC | Change WRE Mode | Mode change from MAINTENANCE to VERIFICATION at ZDV WRS WRE-A initiated. | ZDV WRS Upgrade
2020-05-19 01:43 | NOC | Change WRE Mode | Mode change from VERIFICATION to NORMAL at ZDV WRS WRE-A initiated. | ZDV WRS Upgrade
2020-05-19 15:48 | POC | Software Configuration Check | Operator selected W7.297L as the next startup version at FAI WRS WRE-A. | FAI WRS Upgrade
2020-05-19 15:48 | POC | Change WRE Mode | FAI WRS WRE-A NORMAL MAINTENANCE | FAI WRS Upgrade
2020-05-19 15:49 | POC | Restart | node FAI WRS WRE-A mode 3 current version W7.235L | FAI WRS Upgrade
2020-05-19 16:11 | POC | Change WRE Mode | FAI WRS WRE-A MAINTENANCE VERIFICATION | FAI WRS Upgrade
2020-05-19 16:37 | POC | Change WRE Mode | FAI WRS WRE-A VERIFICATION NORMAL | FAI WRS Upgrade